## Product Backlog
SL | Sprint | Sprint Start date -Sprint End date | Team Memebers | Sprint Goal | Task Planned | Task Completed | Delivarables | Assignee | Status
1 | Sprint 1 | 5 Nov 2025 – 11 Nov 2025 | Misba Shaikh, Ankur Sharma | Requirement analysis and project planning | Requirement gathering, problem understanding, system scope definition, tech stack finalization | Requirements documented, architecture drafted | Requirement Specification, High-level Architecture | Syed Mahmood | Completed
2 | Sprint 2 | 12 Nov 2025 – 18 Nov 2025 | Roshini, Yaswanth | Knowledge base design and data preparation | Knowledge base schema design, sample ticket and article collection | Data schema finalized, initial dataset prepared | Structured knowledge base, sample data | Syed Mahmood | Completed
3 | Sprint3 | 19 Nov 2025 – 25 Nov 2025 | Misba Shaikh, Roshini | Automated categorization and tagging | NLP-based classification, auto-tag logic implementation | Auto-tagging engine implemented | Categorized and tagged knowledge base | Syed Mahmood | Completed
4 | Sprint 4 | 26 Nov 2025 – 2 Dec 2025 | Misba Shaikh, Yaswanth | Real-time article recommendation | Ticket analysis, article matching, ranking logic | Recommendation system working | Ticket-to-article recommendation module | Syed Mahmood | Completed
5 | Sprint 5 | 3 Dec 2025 - 9 Dec 2025 | Ankur Sharma, Yaswanth | Accuracy improvement and feedback handling | Usage tracking, recommendation refinement | Improved relevance and response quality | Optimized recommendation engine | Syed Mahmood | Completed
6 | Sprint 6 | 10 Dec 2025 – 16 Dec 2025 | Roshini, Yaswanth | Content gap detection | Usage analytics, gap identification logic | Content gap detection implemented | Gap analysis reports | Syed Mahmood | Completed
7 | Sprint 7 | 17 Dec 2025 – 23 Dec 2025 | Misba Shaikh, Ankur Sharma | Integration and reporting | Tool integration, dashboard creation | Reporting dashboard functional | Integrated system with reports | Syed Mahmood | Completed
8 | Sprint 8 | 24 Dec 2025 – 5 Jan 2026 | Misba Shaikh, Ankur Sharma, Roshini, Yaswanth | Testing, optimization and documentation | Testing, bug fixing, documentation | Stable system and documents prepared | Final application, documentation | Syed Mahmood | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: Imported Author: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: Imported Author: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: Imported Author: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: Imported Author: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: Imported Author: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: Imported Author: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: Imported Author: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: Imported Author: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: Imported Author: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: Imported Author: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: Imported Author: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: Imported Author: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: Imported Author: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: Imported Author: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: Imported Author: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: Imported Author: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: Imported Author: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7